Project Planning Phase: Project Planning Template

Team ID: 6aba02338343c5cff06282d4

Project Name: EduGenie: AI-Powered Adaptive Learning & Study Material Generation Assistant

1. Product Backlog, Sprint Schedule, and Estimation

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | User Authentication | USN-1 | As a user, I can register using email and password. | 2 | High | All Team Members |
| Sprint-1 | User Authentication | USN-2 | As a user, I can log into the application with my credentials. | 1 | High | All Team Members |
| Sprint-1 | User Authentication | USN-3 | As a user, I can register using Google/Gmail OAuth. | 2 | Medium | Team Member 1 |
| Sprint-1 | Environment & API Setup | USN-4 | As a developer, I can configure Google Cloud API keys and Gemini 1.5 Flash Pro integration. | 3 | High | Team Member 2 |
| Sprint-1 | Core API Architecture | USN-5 | As a developer, I can set up the FastAPI service layer with CORS and routing. | 3 | High | Team Member 3 |
| Sprint-1 | Application UI Framework | USN-6 | As a user, I can view the landing page and navigation dashboard. | 2 | High | Team Member 4 |
| Sprint-2 | Syllabus & Notes Planner | USN-7 | As a user, I can input my subject, grade level, and topics to generate AI study notes. | 5 | High | Team Member 1 & 2 |
| Sprint-2 | Syllabus & Notes Planner | USN-8 | As a user, I can view key concept summaries generated by Gemini AI. | 3 | High | Team Member 2 |
| Sprint-2 | Reference Curation | USN-9 | As a user, I can access automatically generated study links for Khan Academy, Coursera, and Google Scholar. | 3 | Medium | Team Member 3 |
| Sprint-2 | Dashboard UI | USN-10 | As a user, I can access input forms for notes and quiz planning from the dashboard. | 2 | High | Team Member 4 |
| Sprint-3 | Quiz Planner | USN-11 | As a user, I can select difficulty level, topic, and number of questions to generate custom quizzes. | 5 | High | Team Member 1 & 3 |
| Sprint-3 | Quiz Planner | USN-12 | As a user, I can view structured multiple-choice questions with answer keys and explanations. | 4 | High | Team Member 2 |
| Sprint-3 | Visual Study Assistant | USN-13 | As a user, I can upload images of textbook pages or diagrams for AI analysis. | 5 | High | Team Member 3 & 4 |
| Sprint-3 | Multimodal Integration | USN-14 | As a user, I can receive extracted text and visual explanations from uploaded diagrams. | 4 | High | Team Member 2 |
| Sprint-4 | History & Storage | USN-15 | As a user, I can view my previously generated notes and quizzes. | 3 | Medium | Team Member 1 |
| Sprint-4 | Error Handling & Validation | USN-16 | As a system, unparsed AI outputs and API errors should trigger fallback responses. | 3 | High | Team Member 2 |
| Sprint-4 | UI/UX Refinement | USN-17 | As a user, I can view responsive cards and dynamic output formatting. | 3 | Medium | Team Member 4 |
| Sprint-4 | Testing & Deployment | USN-18 | As a developer, I can perform end-to-end scenario testing and latency optimizations. | 4 | High | All Team Members |

2. Project Tracker, Velocity & Burndown Chart

Project Tracker

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 13 | 6 Days | 24 Feb 2025 | 01 Mar 2025 | 13 | 01 Mar 2025 |
| Sprint-2 | 13 | 6 Days | 03 Mar 2025 | 08 Mar 2025 | 13 | 08 Mar 2025 |
| Sprint-3 | 18 | 6 Days | 10 Mar 2025 | 15 Mar 2025 | 18 | 15 Mar 2025 |
| Sprint-4 | 13 | 6 Days | 17 Mar 2025 | 22 Mar 2025 | 13 | 22 Mar 2025 |

Velocity Calculation

Velocity per Day (AV)=Total Story Points CompletedSprint Duration in Days

- Sprint-1 AV: 13 points6 days=2.17 points/day

- Sprint-2 AV: 13 points6 days=2.17 points/day

- Sprint-3 AV: 18 points6 days=3.00 points/day

- Sprint-4 AV: 13 points6 days=2.17 points/day

- Average Team Velocity: 2.38 story points per day (or 14.25 points per 6-day sprint)

Burndown Chart Summary Data

| Timeline | Total Remaining Story Points (Planned) | Actual Remaining Story Points |
| --- | --- | --- |
| Project Start | 57 | 57 |
| End of Sprint-1 | 44 | 44 |
| End of Sprint-2 | 31 | 31 |
| End of Sprint-3 | 13 | 13 |
| End of Sprint-4 | 0 | 0 |

3. References

- https://www.atlassian.com/agile/project-management

- https://www.atlassian.com/agile/tutorials/how-to-do-scrum-with-jira-software

- https://www.atlassian.com/agile/tutorials/epics

- https://www.atlassian.com/agile/tutorials/sprints

- https://www.atlassian.com/agile/project-management/estimation

- https://www.atlassian.com/agile/tutorials/burndown-charts